## Common
Module Code
Test requirement
Tester
Pass | Fail | Untested | N/A | Number of Test cases
0 | 0 | 9 | 0 | 9
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
Search by name
[-] | When user search | 1. Enter the website 2. Input "Hanoi" into search text box 3. Click Search or press Enter | 1.Homepage is displayed 2. "Hanoi" is displayed in search text box 3. Search Result page is displayed
[-1] | When user search | 1. Enter the website 2. Input "" into search text box 3. Click Search or press Enter | 1.Homepage is displayed 2. "" is displayed in search text box 3. Search Result page is displayed | [-]
| When user search | 1. Enter the website 2. Input [maxlength] characters into search text box 3. Click Search or press Enter | 1.Homepage is displayed 2. Input data is displayed in search text box 3. Search Result page is displayed
| When user search | 1. Enter the website 2. Input [maxlength+1] characters into search text box 3. Click Search or press Enter | 1.Homepage is displayed 2. First [maxlength] of input data is displayed in search text box 3. Search Result page is displayed
Help center
| When user view Basic Guide page | 1. Enter the website 2. Click Basic Guide in footer | 1. Homepage page is displayed 2. Basic Guide page is displayed
| When user search a question in basic guide | 1. Enter the website 2. Click Basic Guide in footer 3. Input "How to use website" to search text box 4. Click Search or press Enter | 1. Homepage page is displayed 2. Basic Guide page is displayed 3. "How to use website" is displayed in search text box 4. Scroll to question
| When user search a question in basic guide | 1. Enter the website 2. Click Basic Guide in footer 3. Input "" to search text box 4. Click Search or press Enter | 1. Homepage page is displayed 2. Basic Guide page is displayed 3. "" is displayed in search text box 4. Scroll to first question
| When user search a question in basic guide | 1. Enter the website 2. Click Basic Guide in footer 3. Input [maxlength] characters to search text box 4. Click Search or press Enter | 1. Homepage page is displayed 2. Basic Guide page is displayed 3. [maxlength] characters is displayed in search text box 4. Message "Nothing found" is displayed
| When user search a question in basic guide | 1. Enter the website 2. Click Basic Guide in footer 3. Input [maxlength+1] characters to search text box 4. Click Search or press Enter | 1. Homepage page is displayed 2. Basic Guide page is displayed 3. First [maxlength] characters is displayed in search text box 4. Message "Nothing found" is displayed
Note on F8: Pass Fail Untested N/A

## User
Module Code
Test requirement
Tester
Pass | Fail | Untested | N/A | Number of Test cases
0 | 0 | 135 | 0 | 135
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
Login
Login 1 | When user enter website | 1. Enter the website | 1. Homepage is displayed includes: - Header - Slider - Suggest bar - Post thumbnails - Footer
Login 2 | When user login | 1. Enter the website 2. Click Login button | 1. Homepage is displayed 2. Login panel is displayed include: - Login button - Register button - Login with Facebook button - Login with Google button - User Name text box - Password text box - Remember check box - Login button - Forgot Password hyperlink | Login 1
Login 3 | When user login | 1. Enter the website 2. Click Login in header 3. Input: - "user1@gmail.com" to User Name text box - "user1" to Password textbox 4. Click Login or press Enter | 1. Homepage is displayed 2. Login form is displayed 3. "user1@gmail.com" is displayed in user name text box •••••••••••• is displayed in password text box 4. User is logged in | Login 2
Login 4 | When user login | 1. Enter the website 2. Click Login in header 3. Input: - "" to User Name text box - "" to Password text box | 1. Homepage is displayed 2. Login form is displayed 3. "" is displayed in user name text box "" is displayed in password text box 4. Message "Please enter user name" is displayed below user name text box Message "Please enter password is displayed below password text box Login button is disabled | Login 2
Login 5 | When user login | 1. Enter the website 2. Click Login in header 3. Input: - "user1" to User Name text box - "u" to Password text box 4. Click Login or press Enter | 1. Homepage is displayed 2. Login form is displayed 3. "user1" is displayed in user name text box •••••••••••• is displayed in password text box 4. Message "Please enter a valid email address" is displayed below User Name text box Message "Must be between 5 and 50 characters" is displayed below Password text box Login button is disabled | Login 2
Login 6 | When user login | 1. Enter the website 2. Click Login in header 3. Input: - "user0@gmail.com" to User Name text box - "user0" to Password text box 4. Click Login or press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. User is not logged in | Login 2
Homepage
Homepage 1 |  | 1. Click Website logo | 1. Reload Homepage | Login 3
Homepage 2 |  | 1. Click Search bar | 1. Search page is displayed include: - Search text box - Search button - People - Popular - Recent | Login 3
Homepage 3 |  | 1. Click Friend button in Header | 1. Friend menu is displayed include: - Friend menu items - See All button | Login 3
Homepage 4 |  | 1. Click Notification button in Header | 1. Notification menu is displayed include: - Notification menu items - See All button | Login 3
Homepage 5 |  | 1. Click Message button in Header | 1. Message menu is displayed include: - Message menu items - See All button | Login 3
Homepage 6 |  | 1. Click Avatar button in Header | 1. User menu is displayed include: - View Profile menu item - Logout menu item | Login 3
Homepage 7 |  | 1. Click Wishlist | 1. Homepage is displayed 2. Wishlist page is displayed include: - Header - Suggest bar - Place thumbnails - Footer | Login 3
Homepage 8 |  | 1. Click Look Around | 1. Hompage is displayed 2. Look Around page is displayed include: - Header - Map - Result thumbnails - Footer | Login 3
Homepage 9 |  | 1. Mouse over a post thumbnail | 1. Buttons are displayed: - Add to Wishlist button - Like button - Dislike button | Login 3
Homepage 10 |  | 1. Click a post thumbnail | 1. Post page is displayed include: - Header - User Avatar image - User Name hyperlink - Post Information label - Post content label - Like button - Dislike button - Share button - Comment hyperlink - Comments - Comment text box | Login 3
Homepage 11 |  | 1. Click Create Post | 1. Create Post panel is displayed include: - Update Status label - Post Content text area - Location button - Photo button - Video button - Privacy dropdown button | Login 3
Suggest
1 | When user see place suggestion | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Place Suggestion in Suggestion Bar | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. 5 places is displayed in Suggestion Bar |  |  |  | Chưa code. Sẽ bổ sung
2 | When user see friend suggestion | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Friend Suggestion in Suggestion Bar | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. 5 users is displayed in Suggestion Bar |  |  |  | Chưa code. Sẽ bổ sung
3 | When user see activity suggestion | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Activity Suggestion in Suggestion Bar | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. 5 activities is displayed in Suggestion Bar |  |  |  | Chưa code. Sẽ bổ sung
3 | Social - Personal Page
Personal Page 1 | When user see Timeline | 1. Click View Profile in header | 1. Profile is displayed | Homepage 6
#VALUE! | When user see New Feed | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed in header | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed |  |  |  | Chưa code. Sẽ bổ sung
#VALUE! | Social - Post - Create Post
#VALUE! | When user create a post | 1. Input "Create a post" into text box 2. Click Post | 1. "Create a post" is displayed in text box 2. New post is displayed | Homepage 11
#VALUE! | When user create a post | 1. Input "" into text box 2. Click Post | 1. "" is displayed in text box 2. Popup "Write something" is displayed | Homepage 11
#VALUE! | When user mention a place | 1. Input "" into text box 2. Click Place 3. Input "A" into place text box 4. Click Post | 1. "" is displayed in text box 2. Place text box is displayed 3. "A" is displayed in place text box Suggestion is displayed below place text box 4. Popup "Write something" is displayed | Homepage 11
#REF! | When user mention a place | 1. Input "Create a post" into text box 2. Click Place 3. Input "" into place text box 4. Click Post | 1. "Create a post" is displayed in text box 2. New post is displayed 3. "" is displayed in place text box 4. New post is created | Homepage 11
#REF! | When user mention a place | 1. Input "Create a post" into text box 2. Click Place 3. Input "A" into place text box 4. Click a suggestion 5. Click Post | 1. "Create a post" is displayed in text box 2. New post is displayed 3. "A" is displayed in place text box Suggestion is displayed 4. Choose place is displayed in place text box. Place text box is disabled 5. New post is displayed with place mention | Homepage 11
#REF! | When user mention a friend | 1. Input "Tag a friend +A" into text box 2. Click a friend's name 3. Click Post | 1. "Tag a friend +A" is displayed in text box Suggestion is displayed 2. "+A" is replaced with friend's name hyperlink 3. New post is created with friend mention | Homepage 11
#REF! | When user mention a friend | 1. Input "+A" into text box 2. Click Post | 1. "+A" is displayed in text box 2. New post is displayed | Homepage 11
#REF! | When user mention friends | 1. Input "Tag friends" into text box 2. Input "+A" into text box 3. Click a suggestion 4. Input "+B" friend text box 5. Click a suggestion 6. Click Post | 1. "Tag a friend" is displayed in text box 2. "Tag a friend +A" is displayed in friend text box Suggestion is displayed 3. "+A" is replaced with chosen friend's name 4. "[tagged friend name]+B" is displayed in friend text box Suggest is displayed 5. "+B" is replaced with chosen friend's name 6. New post is displayed with friends mention | Homepage 11
#REF! | When user mention a place | 1. Input "Create a post" into text box 2. Click Add Place 3. Input "A" into place text box 4. Click a suggestion 5. Delete choose place 11. Click Post | 1. "Create a post" is displayed in text box 2. New post is displayed 3. Suggest 10 place which contains "A" is displayed 4. Choose place is displayed in place text box. Place text box is disabled 5. "" is displayed in place text box. Place text box is enabled 11. New post is displayed | Homepage 11
#REF! | When user mention a friend | 1. Input "Tag a friend +A" into text box 2. Click a friend's name 3. Delete friend's name 4. Click Post | 1. "Tag a friend +A" is displayed in text box Suggestion is displayed 2. "+A" is replaced with friend's name hyperlink 3. Friend's name hyperlink is deleted. "Tag a friend" is displayed 3. New post is created without friend mention | Homepage 11
#REF! | When user create a post | 1. Input [maxlength] characters into text box 7. Click Post | 1. [maxlength] characters is displayed in text box 2. New post is displayed | Homepage 11
#REF! | When user create a post | 1. Input [maxlength+1] characters into text box 2. Click Post | 1. First [maxlength] characters is input in text box 2. New post is displayed | Homepage 11
#REF! | When user create a post | 1. Click Cancel | 1. Create Post panel is closed | Homepage 11
#REF! | Social - Post - Edit Post
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit post 4. Delete old data and input "Edit this post" into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. "Edit this post" is displayed 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2 . Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input [maxlength] characters into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. [maxlength] characters is displayed 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2 . Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input [maxlength+1] characters into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. First [maxlength] characters is input 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input "" into post text box | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled 4. "" is displayed in post text box. Edit button is disabled | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Click Cancel | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. Post content label is displayed instead of Post text box. Post is not edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click out of menu | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Menu is closed | Personal page 1
#REF! | Social - Post - Delete Post
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Delete post in menu 4. Click OK | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Confirm popup is displayed include: - Content label - OK button - Cancel button 4. Popup is closed. Post is deleted | Personal page 1
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Delete post in menu 4. Click Cancel | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Confirm popup is displayed include: - Content label - OK button - Cancel button 4. Popup is closed | Personal page 1
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click out of menu | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Menu is closed | Personal page 1
#REF! | Social - Photo - Add Photo
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Photo 3. Choose a [size range] MB jpg file 4. Click Create Post | 1. "Create a post" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. New post with photo is displayed | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Add Photo 3. Choose a [size range] MB jpg file 4. Click X in high right corner of thumbnail 5. Click Create Post | 1. "Create a post" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Image thumbnail is deleted 5. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "" into text box 2. Click Add Photo 3. Choose a [size range] MB jpeg file 4. Click Create Post | 1. "" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "" into text box 2. Click Add Photo 3. Choose a [size range] MB png file 4. Click Create Post | 1. "" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "" into text box 2. Click Add Photo 3. Choose a [size range] MB bmp file 4. Click Create Post | 1. "" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "" into text box 2. Click Add Photo 3. Choose a [size range] MB jpg file 4. Click Create Post | 1. "" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Add Photo 3. Choose a [maxsize] MB jpg file 4. Click Create Post | 1. "Create a post" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Add Photo 3. Choose a [maxsize+1] MB jpg file | 1. "Create a post" is displayed in text box 7. File chooser is displayed 8. Popup "File must be JPG JPEG PNG BMP and less than [size range] MB" is displayed. No thumbnail is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Add Photo 3. Choose an exe file | 1. "Create a post" is displayed in text box 2. File chooser is displayed 3. Popup "File must be JPG JPEG PNG BMP and less than [size range] MB" is displayed. No thumbnail is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | When user create a post with photo | 1. Input "Create a post" into text box 2. Click Add Photo 3. Choose a [size range] MB jpg file 4. Choose an exe file 5. Click Post | 1. "Create a post" is displayed in text box 2. File chooser is displayed 3. Image thumbnail is displayed 4. Popup "File must be JPG JPEG PNG BMP and less than [size range] MB" is displayed. No more thumbnail is created 5. Post is created | Homepage 11 |  |  | Đã sửa case. Chờ sửa code
#REF! | Social - Photo - Edit Photo Caption
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit post 4. Delete old data and input "Edit this post" into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. "Edit this post" is displayed 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2 . Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input [maxlength] characters into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. [maxlength] characters is displayed 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2 . Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input [maxlength+1] characters into post text box 5. Click Edit | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. First [maxlength] characters is input 5. Post content label is displayed instead of Post text box. Post content is edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Delete old data and input "" into post text box | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled 4. "" is displayed in post text box. Edit button is disabled | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Edit in menu 4. Click Cancel | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Post text box is shown and filled instead of Post content label 4. Post content label is displayed instead of Post text box. Post is not edited | Personal page 1
#REF! | When user edit post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click out of menu | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Menu is closed | Personal page 1
#REF! | Social - Photo - Delete Photo
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Delete post in menu 4. Click OK | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Confirm popup is displayed include: - Content label - OK button - Cancel button 4. Popup is closed. Post is deleted | Personal page 1
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click Delete post in menu 4. Click Cancel | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Confirm popup is displayed include: - Content label - OK button - Cancel button 4. Popup is closed | Personal page 1
#REF! | When user delete post while viewing Timeline | 1. Click a post 2. Click downarrow in high-right corner of a post 3. Click out of menu | 1. Post page is displayed 2. Display a menu include: - Edit post menu item - Delete post menu item 3. Menu is closed | Personal page 1
#REF! | When user delete post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Delete in menu 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Confirm popup "Delete this post?" is displayed 9. Close popup
#REF! | Social - Video - Add Video
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "Create a post" into text box 7. Click Add Video 8. Input [youtube link] 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "Create a post" is displayed in text box 7. Text box popup is displayed 8. [youtube link] is displayed 9. Popup is closed. Video thumbnail is displayed 10. New post is displayed. Embedded video is playable |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "" into text box 7. Click Add Video 8. Input [youtube link] 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "" is displayed in text box 7. Text box popup is displayed 8. [youtube link] is displayed 9. Popup is closed. Video thumbnail is displayed 10. New post is displayed. Embedded video is playable |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "" into text box 7. Click Add Video 8. Input [non-youtube link] 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "" is displayed in text box 7. Text box popup is displayed 8. [non-youtube link] is displayed 9. Popup is closed. Input link is displayed as hyperlink 10. New post is displayed |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "" into text box 7. Click Add Video 8. Input "" 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "" is displayed in text box 7. Text box popup is displayed 8. "" is displayed 9. Popup is closed 10. Message "Write something" is displayed |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "Create a post" into text box 7. Click Add Video 8. Input "" 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "Create a post" is displayed in text box 7. Text box popup is displayed 8. "" is displayed 9. Popup is closed. 10. New post is displayed. |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "Create a post" into text box 7. Click Add Video 8. Input [non-youtube link] 9. Click OK 10. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "Create a post" is displayed in text box 7. Text box popup is displayed 8. [non-youtube link] is displayed 9. Popup is closed. Message "Only embedded youtube video is playable" is displayed. Input link is displayed in post text box as hyperlink. 10. New post is displayed. |  |  |  | Chưa edit
#REF! | When user create a post with video | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Create Post 6. Input "Create a post" into text box 7. Click Add Video 8. Input [youtube link] 9. Click OK 10. Click X in high right corner of video thumbnail 11. Click Create Post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Add Post page is displayed 6. "Create a post" is displayed in text box 7. Text box popup is displayed 8. [youtube link] is displayed 9. Popup is closed. Video thumbnail is displayed 10. Video thumbnail is deleted 11. New post is displayed |  |  |  | Chưa edit
#REF! | Social - Video - Edit Video Caption
#REF! | When user edit post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Edit in menu 8. Delete old data and input "Edit this post" into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. "Edit this post" is displayed 9. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | When user edit post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Edit in menu 8. Delete old data and input [maxlength] characters into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. [maxlength] characters is displayed 9. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | When user edit post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Edit in menu 8. Delete old data and input [maxlength+1] characters into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. First [maxlength] characters is input 9. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | When user edit post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Edit in menu 8. Delete old data and input "" into post text box | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. "" is displayed in post text box. Edit button is disabled |  |  |  | Chưa edit
#REF! | When user edit post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Edit in menu 8. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. Post text box is hidden. Post is not edited |  |  |  | Chưa edit
#REF! | When user edit post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Edit in menu 9. Delete old data and input "Edit this post" into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. "Edit this post" is displayed 10. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | When user edit post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Edit in menu 9. Delete old data and input "" into post text box | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. "" is displayed. Edit button is disabled |  |  |  | Chưa edit
#REF! | When user edit post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Edit in menu 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. Post text box is hidden. Post is not edited |  |  |  | Chưa edit
#REF! | When user edit post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Edit in menu 9. Delete old data and input [maxlength] characters into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. [maxlength] characters is displayed 10. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | When user edit post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Edit in menu 9. Delete old data and input [maxlength+1] characters into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. First [maxlength] characters is input 10. Post text box is hidden. Edited post is displayed |  |  |  | Chưa edit
#REF! | Social - Video - Delete Video
#REF! | When user delete post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Delete in menu 8. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Confirm popup "Delete this post?" is displayed 8. Close popup. Post is no longer visible |  |  |  | Chưa edit
#REF! | When user delete post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a post 7. Click Delete in menu 8. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Confirm popup "Delete this post?" is displayed 8. Close popup |  |  |  | Chưa edit
#REF! | When user delete post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Delete in menu 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Confirm popup "Delete this post?" is displayed 9. Close popup. Post is no longer visible |  |  |  | Chưa edit
#REF! | When user delete post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a post 8. Click Delete in menu 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Confirm popup "Delete this post?" is displayed 9. Close popup |  |  |  | Chưa edit
#REF! | Social - Share - Share Post
#REF! | When user share a post | 1. Click Share in a post thumbnail 2. Input "Share this post" into share text box 3. Click OK | 1. Display share panel include: - Share text box - Post content label - Share button - Cancel button 2. "Share this post" is displayed in share text box 3. Text box is closed | Login 1
#REF! | When user share a post | 1. Click Share in a post thumbnail 2. Input "" into share text box 3. Click OK | 1. Display share panel include: - Share text box - Post content label - Share button - Cancel button 2. "" is displayed in share text box 3. Text box is closed | Login 1
#REF! | Social - Comment - Comment
#REF! | When user comment | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Input "Comment this post" into comment text box 7. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. "Comment this post" is displayed in comment text box 7. Comment is created
#REF! | When user comment | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Input [maxlength] characters into comment text box 7. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. [maxlength] characters is displayed in comment text box 7. Comment is created
#REF! | When user comment | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Input [maxlength+1] characters into comment text box 7. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. First [maxlength] characters is input in comment text box 7. Comment is created
#REF! | Social - Comment - Edit Comment
#REF! | When user edit comment while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Edit in menu 8. Delete old data and input "Edit this post" into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. "Edit this post" is displayed 9. Post text box is hidden. Edited post is displayed
#REF! | When user edit comment while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Edit in menu 8. Delete old data and input [maxlength] characters into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. [maxlength] characters is displayed 9. Post text box is hidden. Edited post is displayed
#REF! | When user edit comment while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Edit in menu 8. Delete old data and input [maxlength+1] characters into post text box 9. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. First [maxlength] characters is input 9. Post text box is hidden. Edited post is displayed
#REF! | When user edit comment while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Edit in menu 8. Delete old data and input "" into post text box | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. "" is displayed in post text box. Edit button is disabled
#REF! | When user edit comment while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Edit in menu 8. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Post text box is shown and filled 8. Post text box is hidden. Post is not edited
#REF! | When user edit comment while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Edit in menu 9. Delete old data and input "Edit this post" into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. "Edit this post" is displayed 10. Post text box is hidden. Edited post is displayed
#REF! | When user edit comment while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Edit in menu 9. Delete old data and input "" into post text box | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. "" is displayed. Edit button is disabled
#REF! | When user edit comment while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Edit in menu 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. Post text box is hidden. Post is not edited
#REF! | When user edit comment while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Edit in menu 9. Delete old data and input [maxlength] characters into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. [maxlength] characters is displayed 10. Post text box is hidden. Edited post is displayed
#REF! | When user edit comment while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Edit in menu 9. Delete old data and input [maxlength+1] characters into post text box 10. Click Edit | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Post text box is shown and filled 9. First [maxlength] characters is input 10. Post text box is hidden. Edited post is displayed
#REF! | Social - Comment - Delete Comment
#REF! | When user delete post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Delete in menu 8. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Confirm popup "Delete this post?" is displayed 8. Close popup. Post is no longer visible
#REF! | When user delete post while viewing Timeline | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Timeline 6. Click downarrow in high-right corner of a comment 7. Click Delete in menu 8. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Timeline is displayed 6. Display a menu 7. Confirm popup "Delete this post?" is displayed 8. Close popup
#REF! | When user delete post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Delete in menu 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Confirm popup "Delete this post?" is displayed 9. Close popup. Post is no longer visible
#REF! | When user delete post while viewing Post Detail | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Profile 6. Click Post Detail 7. Click downarrow in high-right corner of a comment 8. Click Delete in menu 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Profile is displayed 6. Post Detail is displayed 7. Display a menu 8. Confirm popup "Delete this post?" is displayed 9. Close popup
#REF! | Social - Like
#REF! | When user like a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Like in bottom-left corner of a post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Like button is hidden, Unlike button is displayed. Like number of this post is increased by one.
#REF! | When user unlike a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Unike in bottom-left corner of a liked post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Unlike button is hidden, Like button is displayed. Like number of this post is decreased by one.
#REF! | When user dislike a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Dislike in bottom-left corner of a post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Dislike button is hidden, Undislike button is displayed. Dislike number of this post is increased by one.
#REF! | When user undislike a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Un-Dislike in bottom-left corner of a disliked post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Un-Dislike button is hidden, Dislike button is displayed. Dislike number of this post is decreased by one.
#REF! | When user like a disliked post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Like in bottom-left corner of a disliked post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Like button is hidden, Unlike button is displayed. Undislike button is hidden, Dislike button is displayed. Like number of this post is increased by one. Dislike number of this post is decreased by one
#REF! | When user dislike a liked post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click Dislike in bottom-left corner of a liked post | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Unlike button is hidden, Like button is displayed.Dislike button is hidden, Undislike button is displayed. Like number of this post is decreased by one. Dislike number of this post is increased by one
#REF! | Social - Report - Report Post
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Spam 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Spam radio button is choose 9. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Rule Violation 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Rule violation radio button is choose 9. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Other 9. Input "" to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. "" is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Other 9. Input "Report this post" to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. "Report this post" is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Other 9. Input [maxlength] characters to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. [maxlength] characters is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 8. Click Other 9. Input [maxlength+1] characters to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. First [maxlength+1] characters is input to Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a post | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Click downarrow in high-right corner of a non-owned post 7. Click Report 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. Menu is displayed 7. Report popup is displayed 8. Spam radio button is choose 9. Popup is closed
#REF! | Social - Report - Report User
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Spam 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User User Menu is displayed 7. Report popup is displayed 8. Spam radio button is choose 9. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Rule Violation 9. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Rule violation radio button is choose 9. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Other 9. Input "" to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. "" is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Other 9. Input "Report this post" to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. "Report this post" is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Other 9. Input [maxlength] characters to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. [maxlength] characters is displayed in Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 8. Click Other 9. Input [maxlength+1] characters to text box 10. Click OK | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Other radio button is choose. Reason text box is enabled 9. First [maxlength+1] characters is input to Reason text box 10. Popup is closed. Post is hidden, message "This post has been reported" is displayed instead
#REF! | When user report a user | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Click Report 9. Click Cancel | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User Menu is displayed 7. Report popup is displayed 8. Spam radio button is choose 9. Popup is closed
#REF! | Social - Chat
#REF! | When user chat with others | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Chat 6. Click an user name 7. Input "" to text box 8. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Chat menu is displayed 6. User chat box is displayed 7. "" is displayed in text box 8. No content is sent. Chat box display no message
#REF! | When user chat with others | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Chat 6. Click an user name 7. Input "Chat with user" to text box 8. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Chat menu is displayed 6. User chat box is displayed 7. "Chat with user" is displayed in text box 8. "Chat with user" is displayed in chat box
#REF! | When user chat with others | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Chat 6. Click an user name 7. Input [maxlength] characters to text box 8. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Chat menu is displayed 6. User chat box is displayed 7. [maxlength] characters is displayed in text box 8. [maxlength] characters is displayed in chat box
#REF! | When user chat with others | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Chat 6. Click an user name 7. Input [maxlength+1] characters to text box 8. Press Enter | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Chat menu is displayed 6. User chat box is displayed 7. First [maxlength] characters is input to text box 8. First [maxlength] characters is displayed in chat box
#REF! | Social - Friend
#REF! | When user add friend | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an non-friend user name 7. Click Add Friend | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Add Friend button is visible 7. Add Friend button is hidden. Friend button is visible
#REF! |  | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an user name 7. Move mouse out | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed 7. User menu is closed
#REF! | When user unfriend | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an friend user name 7. Move mouse over Friend button 8. Click Unfriend | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Friend button is visible 7. Friend menu is displayed 8. Friend button is hidden. Add Friend button is visible
#REF! | When user block | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an non-friend user name 7. Click Block | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Block button is visible 7. Post is hidden
#REF! | When user follow | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an non-friend user name 7. Click Follow | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Add Friend button is visible 7. Follow button is displayed as Unfollow
#REF! | When user follow | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an non-friend user name 7. Click Follow | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Follow button is visible 7. Follow button is displayed as Unfollow
#REF! | When user unfollow | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click New Feed 6. Move mouse over an followed user name 7. Click Unfollow | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. New Feed is displayed 6. User menu is displayed. Unfollow button is visible 7. Follow button is displayed as Follow
#REF! | Social - Wish List
#REF! |  | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click Heart image button in a post thumbnail | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Heart button is marked
#REF! |  | 1. Enter the website 2. Click Login in header 3. Input: - User name: [username] - Password: [password] 4. Click Login or press Enter 5. Click a marked Heart image button in a post thumbnail | 1. Homepage is displayed 2. Login form is displayed 3. [username] is displayed in user name text box •••••••••••• is displayed in password text box 4. Homepage is displayed as Member 5. Heart button is unmarked
Note on F8: Pass Fail Untested N/A