## Risk register
No. | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contingency plan | Fall back plan | Deadline | Risk Owner | Probability | Impact | Risk Score | Status
R1 | Key member leaving | The key member leave team | People risk | Conflict in team or company | Conflict in team in a long time, the key member leave | Team building to connect member with each others. Make each member don't want to leave | persuade the key member don't leave the project by talking, meet his/her needs. | Finding replacement and training new members
R2 | Member uncooperating | The member uncooperating with each others | People risk | Conflict between team member | Team member do not willing to work with each others | Team building to connect member with each others. | Finding root conflict (social relationship, private conflict) | Trade-off strategy
R3 | Hardware problems | Hardware is broken because of external cause such as flood, earthquake,… | Technology | External causes | External damage hardware | Hardware replacement | Repair damaged hardware | Buy new
R4 | Data lost | Data lost | Technology | Software, hardware, member | Data lost when software, hardware, synchronizing got problems. | Backup data frequently | Each member should own copies | Re-work
R5 | Plan not meet | Some members of team do not finish their tasks before deadline. | Technology & People | Task is too much. Member's ability is not enough. Data lost when synchronizing. | Team member do not submit their finished tasks in time, or the submitted tasks do not meet the target of tasks. | When forming team, choosing member with suitable ability | Daily meeting to catch progress. Change plan when needed. | Deliver later
R6 | Change requirement | Requirement changed when some functions can not be completed or some technologies is not suitable. | Technology | Functions can not be completed. Technologies is not suitable | Developing phase got problems
Note on B2: Duc Filan: Add risk ở intro và add thêm các risk khác ở đây